## Sheet1
Similar US 281 projects did not appear in the TIP prior to the FY 2000-2003 document
| Project Limits |  | Project Description | Funding Cat | Cost | Let Date
FY 2000-2003 Transportation Improvement Program (Approved June 21, 1999)
US 281 | at Borgfeld Road | - | Construct overpass | STP Safety | 8900000 | September 2002
US 281 | at Evans Road | - | Construct interchange | St. Discr. | 12742135 | September 2002
US 281 | at Stone Oak Parkway | - | Construct interchange | St. Discr. | 8650000 | September 2002
FY 2002-2004 Transportation Improvement Program (Approved April 30, 2001)
US 281 | 0.6 miles N of Loop 1604 | 2.5 miles N of Loop 1604 | Upgrade to 6 lane freeway w/4 lane FR and TMS | STP-MM(S) | 30900000 | September 2003
US 281 | at Borgfeld | - | Reconfigure interchange (grade separation) | STP-Safety | 8900000 | September 2002
US 281 | at Stone Oak Parkway | - | Reconfigure interchange (grade separation) | St. Discr. | 8650000 | September 2003
FY 2004-2006 Transportation Improvement Program (Approved April 28, 2003)
US 281 | 0.6 miles N of Loop 1604 | 2.5 miles N of Loop 1604 | Upgrade to 6 lane freeway w/4 lane FR and TMS | 7 - STP-MM | 25972000 | September 2004
US 281 | at Borgfeld | - | Reconfigure interchange (grade separate) | 8 - Safety | 9300000 | September 2004
US 281 | at Stone Oak Parkway | - | Reconfigure interchange (grade separation) | 11 - Distr Disc | 17247000 | September 2004
FY 2006-2008 Transportation Improvement Program (Approved April 25, 2005)
US 281 | 0.4 Mi N of Loop 1604 | 0.7 Mi N of Stone Oak | Expand to 6 lane expy w/4 lane FR (toll 6 new mainlanes), initial TMS | 2 - Metro Cor | 59500000 | September 2005
US 281 | 2.5 Mi N of Loop 1604 | Comal County Line | Expand to 6 lane expy w/4 lane FR (toll 6 new mainlanes) | 2 - Metro Cor | 81000000 | January 2008
US 281 | at Borgfeld | - | Reconfigure interchange (grade separate) | 11 - Distr Disc | 9300000 | September 2005
US 281 | at Loop 1604 | - | Expand interchange with tolled direct connectors | 2 - Metro Cor | 180000000 | January 2006
FY 2006-2008 Transportation Improvement Program (as of December 1, 2006)
US 281 | 0.4 Mi N of Loop 1604 | 0.7 Mi N of Stone Oak | Expand to 6 lane expy w/4 lane FR (toll 6 new mainlanes), initial TMS | 2 - Metro Cor | 59500000 | September 2005
US 281 | 2.5 Mi N of Loop 1604 | Comal County Line | Expand to 6 lane expy w/4 lane FR (toll 6 new mainlanes) | 2 - Metro Cor | 86000000 | January 2008
US 281 | at Borgfeld | - | Reconfigure interchange (grade separate) | 8 - Safety | 20010016 | August 2007
US 281 | at Loop 1604 | - | Expand interchange with tolled direct connectors | 2 - Metro Cor | 180000000 | January 2008
Note: these entries are as of the approval date shown for each TIP document. More research may be needed to document interim actions between TIP approval dates.